## Slide 1: 3rd Joint Environment and Risk Management Platform
“Enhancing Synergies for a Resilient Tomorrow”
August 30-September 1, 2023
Weno, Chuuk
Yap State Environmental Protection Agency
Jordan S. Mautaman

## Slide 2
“Enhancing Synergies for a Resilient Tomorrow”
Progress since 2018…
  Item 1: Ridge to Reef Project
    Enhanced Management and Capacity building for new and existing Marine Protected Areas and Terrestrial Sanctuaries.
    Project Completed 2022
  Item 2: JPRISM 2
    Revision of SSWMS (Completed)
    Improvements & Expansion of State Recycling Program
      Equipment Acquisition and Operation
      Expansion of Recycling Programs recyclable categories
  Item 3: RENI Project (Disaster Risk Management)
    Water Security Project
      2 EPS sites established
      4 Rainwater Harvesting Systems Installed
      Completed a hydrogeological survey and study for the largest underground Aquifer within the state (Gagil-Tamil Aquifer)
      Project Completed 2020

## Slide 3
“Enhancing Synergies for a Resilient Tomorrow”
Progress since 2018 Continued…
  Item 4: Adaptation Fund Project:
    Project Launched in 2019
  Item 5: PacWaste Project
    Special Programme Proposal (SPREP)
    Project Coordinator Hired
    Project Launched earlier this year…
  Item 6: PAN Regulation and Establishment
    PAN Regulation and Establishment completed by 2020.
    PAN Coordinator Hired
    Program activities overseen by the state R&D.
  Item 7: GEF 7 Program Exercise
    Program Exercise
      Key prioritized areas was being identified by each respective state virtually.

## Slide 4
Ongoing and upcoming projects and activities
  Item 1: PacWASTE Plus Project
    Enhancing capacity for the ongoing composting activities implemented by the R&D’s Agriculture Division.
  Item 2: GEF 6 Project
    Support the activities regarding the Alien Invasive Species (Marine and Terrestrial)
    Activities ongoing…
  Item 3: PAN Activities
    Continued support for community environmental groups
    PAN activities ongoing
  Item 4: Adaptation Fund:
    Continue the implementation of the projects water security component activity.
  Item 5: GEF 7 Project
    Continue to work with the stakeholder on project planning
  Item 6: State Plans
    Finalizing the Yap State Disaster & Risk Management Plan
    Finalizing the State Oil Spill Response Plan
  Item 7: State IDP’s
    Oversee the Environmental Impacts and Aspects of upcoming major infrastructure projects
“Enhancing Synergies for a Resilient Tomorrow”

## Slide 5
Challenges
  Item 1: Global Pandemics i.e. Covid -19
    Hampered the implementation of all ongoing and projected state projects and activities
    Strained the implementation timeline of the aforementioned projects and activities
  Item 2: Project Coordination
    Better coordination between Project Coordinator and Relevant Stakeholders on the efficient implementation of project activities.
“Enhancing Synergies for a Resilient Tomorrow”

## Slide 6
Opportunities for collaboration
  Item 1: Better Planning and Coordination between state entities in response to disaster.
  Item 2: Utilization of better and newer communication mediums i.e. Virtual Conferences
  Item 3: Frequent Coordination between Project Management Team and all relevant state entities/stakeholders on project progress updates and projected activities.
“Enhancing Synergies for a Resilient Tomorrow”

## Slide 7
Recommendations
  Item 1: Improve communication coordination between the National and State Governments.
    Community Involvement in all state project planning
      State support for communities capacity to have an effect on all proposed projects.
“Enhancing Synergies for a Resilient Tomorrow”