## Slide 1: 3rd Joint Environment and Risk Management Platform
“Enhancing Synergies for a Resilient Tomorrow”
August 30-September 1, 2023
Weno, Chuuk
3.5 International Organization for Migration
Ahmadi Gul Mohammad, Deputy Chief of Party, IOM

## Slide 2
“Enhancing Synergies for a Resilient Tomorrow”
Progress since 2018
  93 New houses handed over to beneficiaries under TWRP
  7 Public infrastructure (Repairs & New construction) completed under TWRP.
  In collaboration with DECEM and DCOs, 8 TTX attended by 600 participants
  Assisted 5 policies/legislation/guidelines/SOPs and plans review/update/development focusing on disaster response and/or reconstruction
  4 Essentials of Humanitarian Assistance (EHA) ToT attended by 60 participants
  3 strategic warehouses across FSM with preposition relief supplies
  Trained 257 (155 males, 102 females) community members on climate change adaptation for food and water security
  Engaged 245 community members (145 males, 100 females) and developed 8 Community Disaster Preparedness Plans (CDPPs)
  Organized 4 youth summits, trained 65 youth (31 males, 34 females) on Youth Leadership and climate change adaptation and implemented 8 ‘mini-projects’

## Slide 3
Ongoing and upcoming projects and activities
  Ongoing construction of 4 Public Infrastructure facilities with 23 in queue.
  40 new houses are to be constructed during the coming days and voucher assistance activities are ongoing targeting 228 beneficiaries.
  EHA TOT, TTX, IDA trainings, development of CBI, AAP SOP, warehousing and preposition supplies
  Review and update of the state/national disaster plan and SOP
  Development of Information Management System (IMS) for DCO/DECEM
  Finalizing 8 climate change adaptation and disaster risk reduction interventions in 8 communities across FSM (2 food security, 5 water security and 1 emergency communication)
“Enhancing Synergies for a Resilient Tomorrow”

## Slide 4
Challenges
  Rough weather is impacting the mobilization of staff, delivery of materials and construction activities.
  International procurement and shipment of construction materials takes time as local market has no capacity to fulfill these needs.
“Enhancing Synergies for a Resilient Tomorrow”

## Slide 5
Opportunities for collaboration
  Capacity building, Resilience and DRR initiatives
  Strategic partnership and collaboration at policy and strategic level to enhance preparedness
“Enhancing Synergies for a Resilient Tomorrow”

## Slide 6
Recommendations
  Strengthening Coordination
  Government priority areas on resilience, DRR and climate change adaptation
“Enhancing Synergies for a Resilient Tomorrow”

## Slide 7
“Enhancing Synergies for a Resilient Tomorrow”
Thank you!
Notes: So, as we look forward to the sign off of our Agreement and kick start on our implementation phase of the NAP, we feel the urge to share key recommendations that not only will help better understand what we need to do, but to also fill in the gaps as we move forward in this NAP implementation.